## Sheet1
AI For Good Work Back
Phase 1: Create Curriculum
Work Item | Description | Effort (hrs)
Lesson plan Lesson 1 | Lesson plan - discover the possibities of AI - a tour through cognitive services and AI solutions - build a chat bot | 8
Lesson plan Lesson 2 | Problem Analysis - understanding ecology though tracking animal populations. Search out and aggrigate animal population data | 8
Lesson plan Lesson 3 | Lesson three - build a classifier for image types to tell one animal from all others (polar bear adapted) | 8
Lesson plan Lesson 4 | Test implementation of the Wildlfe services API and write a final paper about how (someone) could use AI or imagine a new AI to provide insights into a problem or help treat or solve a problem. | 8
Section 1 Activities | Write out and test the activities for session one to work in Azure Labs - build a chat bot adaption | 16
Section 2 Activities | Use Azure Labs to aggregate images and store them in blob storage. | 8
Section 3 Activities | Use Azue Labs to create a VM that will run the polar bear lab adaptation to their VM | 24
Section 4 Activities | Use VM to hold the assignment and connect the student with images and the wildlife API and give them an upload location for their final paper in the cloud (can be centralized) | 8
Review Cycle | Time for review/meetings and coms | 12
100
Deliverables
Opsgility repository | While creating the project, a repository will be created under Opsgility in GitHub.
Written Curriculum | Each lesseon will be in markdown in a sub folder of the project and include all instructions for the lessons. The repo will grant the reviewers access to the curriculum to test and verify as the project progresses.
Support Files | Support files for each lesson will live in the same sub folder as the lesson plans
Azure Labs | Templates for the Azure Labs required will also have a folder in the same sub folder with its own readme file for deployment
Final Delivery | Microsoft will create a GitHub Repository and Opsgility will create a branch and put all of the resources in that branch and create a pull request for the Microsoft team to complete.